## Product Roadmap
OLSERA MITRA MODAL 2026 — PRODUCT ROADMAP
Epic-Based Delivery Timeline ¦ Q1 – Q3 2026 ¦ Phase 1: Prototype & Partner Acquisition
Phase | Objective | Key Deliverables | Target Go Live | Revenue Impact | Risk Level | Owner
Phase 1 — Foundation | Monorepo, Tooling & Design System | Monorepo, TypeScript, Docker, Design System, Auth | 1 Mar | — | P0 - Blocker | Product / Engineering
Phase 2 — Merchant Flow | Complete Merchant UX + Partner Redirect Cards | 7 merchant pages, Scoring Engine, Simulation flow, Adapundi redirect, OCBC card | 31 Mar | — | P0 - Blocker | Product / Engineering
Phase 3 — Partner Portal | Partner Decision Layer | Partner dashboard, App review, Approve/Reject, SLA timers | 15 Apr | — | P0 - Critical | Product / Engineering
Phase 4 — Admin & Data | Operations & Analytics Layer | Admin portal, Data Intelligence, Executive Dashboard | 30 Apr | — | P1 - High | Product / Engineering
Phase 5 — Backend APIs | Real API Layer + QA | All endpoints, DB migrations, Seed data, Automated tests | 31 May | — | P1 - High | Product / Engineering
Phase 6 — Partner Integration | Live Partner Integration | Adapundi full API, OCBC integration, Production infrastructure | 30 Jun | Referral fee revenue | P1 - High | Product / Engineering
⚠️ Note — Backoffice version: A separate backoffice application (not this web app) also targets Adapundi + OCBC integration by end of March 2026.
⚠️ Partner dependency (E5, E6, E8, E10): Requires at least one partner to formally commit (signed MOU or equivalent). Without partner willingness, partner-facing portal and SLA mechanics cannot be meaningfully tested or operated end-to-end.
Epic ID | Epic Name | Quarter | Phase | Deadline | Priority | Dependencies | Status
Q1 2026
E1 | Project Foundation & Dev Environment | Q1 | Phase 1 — Foundation | 28 Feb | P0 - Blocker | None (Foundation Epic) | Done
E2 | Design System & Shared Components | Q1 | Phase 1 — Foundation | 1 Mar | P0 - Blocker | E1 (Boilerplate Setup) | Done
E3 | Authentication & RBAC | Q1 | Phase 1 — Foundation | 10 Mar | P0 - Blocker | E2 (Design System) | In Progress
E7 | Scoring & Matching Engine | Q1 | Phase 2 — Merchant Flow | 20 Mar | P0 - Blocker | E1 (DB Schema) | In Progress
E4 | Merchant Flow — Simulation & Application | Q1 | Phase 2 — Merchant Flow | 31 Mar | P0 - Blocker | E3 (Auth), E7 (Scoring) | In Progress (Frontend ✅ · API ⬜)
E12 (Phase 1) | Partner Redirect — Adapundi + OCBC | Q1 | Phase 2 — Merchant Flow | 31 Mar | P0 - Critical | E4 (Merchant Flow) — URL redirect only, no API | Prototype ✅ · Production ⬜
E12 Phase 1: Adapundi redirect + OCBC 'Coming Soon' card — already live in prototype. Production deployment targets end of March. No API integration required.
Q2 2026
E8 | SLA Management | Q1–Q2 | Phase 3 — Partner Portal | 15 Apr | P0 - Critical | E4 (Merchant Submit) + Partner signed MOU ⚠️ | In Progress (Frontend ✅ · API ⬜)
E5 | Partner Portal — Review & Decision | Q1–Q2 | Phase 3 — Partner Portal | 15 Apr | P0 - Critical | E4 (Merchant Flow), E7 (Score) + Partner willingness / signed MOU ⚠️ | ⚠️ Needs Partner MOU
E6 | Admin Portal — Operations & Monitoring | Q2 | Phase 4 — Admin & Data | 30 Apr | P0 - Critical | E5 (Partner), E8 (SLA) + Partner willingness / signed MOU ⚠️ | ⚠️ Needs Partner MOU
E10 | Data Team & Management Views | Q2 | Phase 4 — Admin & Data | 30 Apr | P1 - High | E4 (Merchant), E5 (Partner) + Partner data flowing ⚠️ | ⚠️ Needs Partner MOU
E9 | Database & Seed Data | Q2 | Phase 5 — Backend APIs | 31 May | P0 - Critical | E1 (Migration runner) | In Progress
E11 | Testing & QA | Q2 | Phase 5 — Backend APIs | 31 May | P1 - High | All Epics | Todo
Q2 – Q3 2026
E12 (Phase 2) | Partner API Integration (Full — Adapundi + OCBC) | Q2–Q3 | Phase 6 — Partner Integration | 30 Jun | P0 - Critical | E5 (Partner Portal) + API docs + sandbox from Adapundi + OCBC ⚠️ | Blocked on API docs
E13 | Production Infrastructure & Security | Q3 | Phase 6 — Partner Integration | 30 Jun | P0 - Critical | E11 (Tests), E12 Phase 2 (APIs) | Phase 2

## Epic Timeline
OLSERA MITRA MODAL 2026 — EPIC TIMELINE
Visual Epic Delivery Timeline ¦ March – June 2026 ¦ Q1 – Q3
Epic ID | Epic Name | Quarter | Priority | Status | Target Date | March |  |  |  | April |  |  |  | May |  |  |  | June
[6 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
E1 | Project Foundation & Dev Env | Q1 | P0 - Blocker | Done | 28 Feb
E2 | Design System & Shared Components | Q1 | P0 - Blocker | Done | 1 Mar | bar: March W1 to March W2
E3 | Authentication & RBAC | Q1 | P0 - Blocker | In Progress | 10 Mar
E7 | Scoring & Matching Engine | Q1 | P0 - Blocker | In Progress | 20 Mar | bar: March W2 to March W4
E4 | Merchant Flow — Simulation & Apply | Q1 | P0 - Blocker | In Progress | 31 Mar
E12 Ph.1 | Adapundi Redirect + OCBC Card (→ prod) | Q1 | P0 - Critical | Prototype ✅ · Production ⬜ | 31 Mar | bar: March W3 to March W4
E8 | SLA Management ⚠️ partner MOU | Q1–Q2 | P0 - Critical | ⚠️ Needs Partner MOU | 15 Apr
E5 | Partner Portal ⚠️ partner MOU | Q1–Q2 | P0 - Critical | ⚠️ Needs Partner MOU | 15 Apr | bar: March W3 to April W2
E6 | Admin Portal ⚠️ partner MOU | Q2 | P0 - Critical | ⚠️ Needs Partner MOU | 30 Apr
E10 | Data & Mgmt Views ⚠️ partner MOU | Q2 | P1 - High | ⚠️ Needs Partner MOU | 30 Apr | bar: April W1 to April W4
E9 | Database & Seed Data | Q2 | P0 - Critical | In Progress | 31 May
E11 | Testing & QA | Q2 | P1 - High | Todo | 31 May | bar: May W1 to May W4
E12 Ph.2 | Partner Full API (Adapundi + OCBC) | Q2–Q3 | P0 - Critical | Blocked on API docs | 30 Jun
E13 | Production Infrastructure & Security | Q3 | P0 - Critical | Phase 2 | 30 Jun | bar: June W1 to June W4
LEGEND
Done |  |  |  |  | In Progress | April W1: Todo / Planned; May W2: Phase 1 Redirect ✅
⚠️ Needs Partner MOU |  |  |  |  | Blocked / Phase 2

## Master Timeline (Visual)
OLSERA MITRA MODAL — PROGRAM MASTER TIMELINE 2026
Financial Infrastructure Development & Commercial Rollout
EXECUTIVE PHASE OVERVIEW
PHASE 1 FOUNDATION |  |  | PHASE 2 INTEGRATION |  |  | PHASE 3 COMMERCIALIZATION
Mar – Apr 2026 |  |  | Apr – May 2026 |  |  | Jun – Jul 2026
Core Platform Build |  | → | Backend APIs & Partner Portal |  | → | Merchant Rollout & Monetization
5-portal prototype • Auth • Scoring engine |  |  | All API endpoints live • Partner MOU required |  |  | 1,000 merchants onboarded • Referral fee revenue
Go-Live: Apr '26 |  |  | Go-Live: May '26 |  |  | Go-Live: Jul '26
Risk: Low |  |  | Risk: Medium |  |  | Risk: High
MODULE MILESTONE BREAKDOWN
Milestone | Merchant Flow Engine |  | Scoring Engine | Partner Portal ⚠ |  |  | Admin & Analytics |  | DEPENDENCY MAP
Phase / Period | Status |  | Status | Status |  |  | Status |  | Item | Risk Impact | Owner
Platform Design & Prototyping (Mar – Apr) | ✓ Done |  | ✓ Done | ✓ Done |  |  | ✓ Done |  | Partner API Access | High ⚠ | Product
Engine Dev & API Build (Apr – May) | ▶ Active |  | ▶ Active | ⚠ At Risk |  |  | ▶ Active |  | Data Schema Final. | Medium △ | Engineering
System Testing & QA (May) | ○ Planned |  | ○ Planned | — Blocked |  |  | ○ Planned |  | OJK Compliance | Medium △ | Legal
REVENUE LINKAGE | [8 empty] | REVENUE DASHBOARD
Milestone |  |  | Revenue Unlock |  | Est. Monthly Value |  |  | Status | Milestone | Revenue | Status
Platform Prototype Live |  |  |  |  | Rp — |  |  | Pending | Enables Partners | Rp — | Pending
Backend APIs Live |  |  |  |  | Rp 50jt / mo |  |  | Pending | Pilot Revenue | Rp 50jt / mo | Pending
1,000 Merchants Onboarded |  |  |  |  | Rp 500jt / mo |  |  | At Risk | Full Monetization | Rp 500jt / mo | At Risk
Confidential — Internal Program Governance ¦ Olsera Mitra Modal

## Master Timeline (Table)
OLSERA MITRA MODAL — PROGRAM MASTER TIMELINE 2026
Financial Infrastructure Development & Commercial Rollout
Executive Summary | [11 empty] | Dependencies
Phase | Objective | Key Deliverable | Target Go Live | Revenue Impact | Risk Level | Owner | [5 empty] | Item | Depends On
Phase 1 — Foundation | Core Platform Build | 5-portal prototype live | 30 Apr 2026 | Enables Partner Onboarding | Medium | Product / Engineering | [5 empty] | Partner API Access | External Parties (Adapundi, OCBC)
Phase 2 — Integration | Bank & Partner API Integration | Backend APIs + Partner MOU | 17 May 2026 | Pilot Revenue Start | High | Product / Engineering | [5 empty] | Data Schema Final. | Core Build / E9 DB Migrations
Phase 3 — Commercialization | Merchant Rollout | 1,000 Merchants Onboarded | 30 Jul 2026 | Monetization Start | High | Product / Engineering | [5 empty] | OJK Compliance | Scoring Engine / Legal Review
Module Timeline
Module | Milestone | Owner | Start Date | End Date | Dependency | Status | Mar | Apr | May | Jun | Jul | Item | Impact If Late
Merchant Flow Engine | Core Platform Build | Engineering | 01-Mar-26 | 31-Mar-26 | E1, E2 Foundation | On Track | [5 empty] | Merchant Prototype | On track — no blockers
Scoring Engine | Scoring Model Ready | Engineering | 10-Mar-26 | 20-Mar-26 | E1 DB Schema | In Progress | [5 empty] | Scoring Engine | Delays push merchant API
Partner Portal | Partner Decision Flow | Product | 01-Apr-26 | 15-Apr-26 | E4 + Partner MOU ⚠ | At Risk | [5 empty] | Partner MOU | Portal unusable without partner
Admin & Analytics | Operations Layer | Engineering | 15-Apr-26 | 30-Apr-26 | E5 Partner Portal | On Track | [5 empty] | Partner Portal | Admin blind without data
Backend APIs | Full API Integration | Engineering | 01-May-26 | 31-May-26 | E9 DB + E7 Scoring | Planned | [5 empty] | DB Migrations | All APIs blocked
Partner API Integ. | Adapundi + OCBC Full API | Product | 01-Jun-26 | 30-Jun-26 | API docs from partners ⚠ | Blocked | [5 empty] | Partner API Docs | Integration cannot start
Revenue Linkage
Milestone | Revenue Unlock | Est Monthly Value | Status
Platform Prototype Live | Enables Partner Onboarding | Rp — | GREEN
Backend APIs Live | Pilot Revenue Start | Rp 50jt / mo | YELLOW
1,000 Merchants Onboard | Full Monetization | Rp 500jt / mo | At Risk
Internal — Program Governance Use Only ¦ Olsera Mitra Modal